## Sheet1
Work Breakdown Structure (WBS): Development of FlowDocs – A Web-Based Document Workflow System for SMEs
No. | Activities | Description | Duration (Days) | Start Date | End Date | Responsible
2 | System Development | Full development of the FlowDocs software including coding, interface creation, testing, and deployment. | 80 | 2025-11-17 | 2026-02-04 | Tagalag
2.1 | User Access & Authentication | Development of login, signup, and role-based access for admin and staff. | 10 | 2025-11-17 | 2025-11-27 | Tagalag
2.1.1 | Management Login Interface | Login form for administrators and CEOs to access approval features. | 5 | 2025-11-17 | 2025-11-22 | Tagalag
2.1.2 | Staff Login Interface | Login form for HR, Accounting, and Sales staff with limited access rights. | 5 | 2025-11-22 | 2025-11-27 | Tagalag
2.2 | Dashboard Development | Creation of central dashboards for both admin and department staff. | 12 | 2025-11-27 | 2025-12-09 | Tagalag
2.2.1 | Management Dashboard | Displays pending, approved, and returned files with action shortcuts. | 6 | 2025-11-27 | 2025-12-03 | Tagalag
2.2.2 | Staff Dashboard | Shows submitted files, feedback received, and real-time status updates. | 6 | 2025-12-03 | 2025-12-09 | Tagalag
2.3 | Document Submission & Routing | Core workflow where staff submit files and FlowDocs routes them automatically. | 14 | 2025-12-09 | 2025-12-23 | Tagalag
2.3.1 | Document Upload Interface | Allows staff to upload and label documents by department or purpose. | 7 | 2025-12-09 | 2025-12-16 | Tagalag
2.3.2 | Routing Logic & Email Trigger | Automatically forwards files to assigned reviewers and notifies them by email. | 7 | 2025-12-16 | 2025-12-23 | Tagalag
2.4 | File Validation & Feedback System | Enables reviewers to comment, request changes, or approve submissions. | 10 | 2025-12-23 | 2026-01-02 | Tagalag
2.4.1 | Review Interface | Displays file details, attached notes, and options to return with feedback. | 5 | 2025-12-23 | 2025-12-28 | Tagalag
2.4.2 | Feedback Notification | Sends staff email and dashboard alerts when files are returned or approved. | 5 | 2025-12-28 | 2026-01-02 | Tagalag
2.5 | E-Signature & Authorization | Adds secure digital signing via unique link for authorized personnel. | 8 | 2026-01-02 | 2026-01-10 | Tagalag
2.5.1 | Signature Verification Page | Displays file content for review before digital signing. | 4 | 2026-01-02 | 2026-01-06 | Tagalag
2.5.2 | Signature Recording Function | Saves verified signatures and updates document status as 'Approved.' | 4 | 2026-01-06 | 2026-01-10 | Tagalag
2.6 | File Repository & Department Directory | Secure file storage and retrieval by role and department. | 8 | 2026-01-10 | 2026-01-18 | Tagalag
2.6.1 | Management Repository | Private folder for management with all archived files. | 4 | 2026-01-10 | 2026-01-14 | Tagalag
2.6.2 | Department Repository | Separate folders for HR, Accounting, and Sales staff. | 4 | 2026-01-14 | 2026-01-18 | Tagalag
2.7 | Messaging & Announcement System | Built-in chat and announcement board for internal communication. | 7 | 2026-01-18 | 2026-01-25 | Tagalag
2.7.1 | Staff Messaging Interface | Enables staff to message management or same-department peers. | 3 | 2026-01-18 | 2026-01-21 | Tagalag
2.7.2 | Announcement Board | Management can post updates viewable by all users. | 4 | 2026-01-21 | 2026-01-25 | Tagalag
2.8 | AI Intelligent Search & Classification | Integration of TensorFlow.js for smart document lookup. | 8 | 2026-01-25 | 2026-02-02 | Tagalag
2.8.1 | Search Algorithm Setup | Implement AI-based keyword and content matching. | 4 | 2026-01-25 | 2026-01-29 | Tagalag
2.8.2 | Result Ranking & Interface | Build search results display and ranking logic. | 4 | 2026-01-29 | 2026-02-02 | Tagalag
3 | Testing, Debugging & Deployment | Final integration, functional testing, and deployment to local server. | 9 | 2026-02-02 | 2026-02-11 | Buan
3.1 | Module Testing | Verify all modules and resolve defects. | 4 | 2026-02-02 | 2026-02-06 | Buan
3.2 | System Deployment | Upload to server, final checks, and preparation for defense. | 5 | 2026-02-06 | 2026-02-11 | Buan
4 | Project Documentation / User' Manual | Writing of User Manual and finalizing Project Document | 14 | 2026-02-11 | 2026-02-25 | Tagalag, Buan
4.1 | Chapter 1 | Review and update Chapter 1 | 2 | 2026-02-11 | 2026-02-13 | Tagalag, Buan
4.2 | Chapter 2 | Review and update Chapter 2 | 2 | 2026-02-13 | 2026-02-15 | Tagalag, Buan
4.3 | Chapter 3 | Review and update Chapter 3 | 2 | 2026-02-15 | 2026-02-17 | Tagalag, Buan
4.4 | Chapter 4 | Write Chapter 4 | 2 | 2026-02-17 | 2026-02-19 | Tagalag, Buan
4.5 | Chapter 5 | Write Chapter 5 | 2 | 2026-02-19 | 2026-02-21 | Tagalag, Buan
4.6 | User Manual | Create User’s Manual | 4 | 2026-02-21 | 2026-02-25 | Tagalag, Buan